## Gantt
Task | Duration | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June
|  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
A | 2 | bar: October 1 to October 2
B | 1 | bar: October 3
C | 2 | bar: October 3 to October 4
D | 1 | bar: November 1
E | 1 | bar: November 1
F | 2 | bar: November 1 to November 2
G** | 5 | bar: November 1 to December 1
H | 3 | bar: November 2 to November 4
I | 4 | bar: November 3 to December 2
J | 3 | bar: November 4 to December 2
K | 4 | bar: January 2; February 1 to March 2
L | 4 | bar: February 2 to February 3
M | 4 | bar: February 3 to February 4
N | 4 | bar: February 4
O | 3 | bar: February 4 to March 2
P*** | 6 | bar: March 1 to April 2
Q | 2 | bar: March 3 to April 1
R* | 4 | bar: April 3 to May 2
S** | 1 | bar: May 2

## Task List
ID | Task Description | Start | End | Duration | Type | Colour
A | Complete Project Proposal | Oct W1 | Oct W2 | 2 weeks | On-hold
B | Complete Ethics and Data Management Plan | Oct W3 | Oct W3 | 1 week | Documentation
C | Foundation & Prototyping (Audio Loading, Basic Pitch) | Oct W3 | Oct W4 | 2 weeks | Development
D | Basic Tab Generation (Single Notes & Simple Melodies) | Oct W4 | Oct W4 | 1 week | Testing
E | Multi Track Audio Separation | Nov W1 | Nov W1 | 1 week | Major deadlines | *
F | Improve Tab Generation (Chords, Polyphonic Audio) | Nov W1 | Nov W2 | 2 weeks
G | Write & Submit Interim Report (10% of grade) | Nov W1 | Dec W1 | 5 weeks
H | Implement Sequential Model (CNN Mapping) | Nov W2 | Nov W4 | 3 weeks
I | Model Evaluation | Nov W3 | Dec W2 | 4 weeks
J | Develop End-to-End Model | Nov W4 | Dec W2 | 3 weeks
K | User Interface Development | Jan W2 | Mar W2 | 4 weeks
L | Export Functionality for File Format | Feb W2 | Feb W3 | 3 weeks
M | Traffic Confidence Score System | Feb W3 | Mar W1 | 4 weeks
N | Audio Player and MIDI Player | Mar W1 | Mar W1 | 4 weeks
O | Qualitative Evaluation | Mar W2 | Mar W3 | 3 weeks
P | Write Final Dissertation (75% of grade) | Mar W1 | Apr W2 | 6 weeks
Q | Final Code Polish & Demo Video Creation | Mar W3 | Mar W4 | 2 weeks
R | Prepare Presentation & Demo for Assessment | Apr W3 | May W2 | 4 weeks
S | Final Presentation/Demonstration (15% of grade) | May W2 | May W2 | 1 week