## Gantt
Task | Duration | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June
|  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
A | 2 | bar: October 1 to October 2
B | 1 | bar: October 3
C | 6 | bar: October 3 to November 4
D | 4 | bar: November 3 to December 2
E** | 3 | bar: December 2 to December 4
F | 5 | bar: December 3 to January 2; February 1
G | 4 | bar: February 2 to March 1
H | 3 | bar: March 2 to March 4
I | 2 | bar: April 1 to April 2
J | 3 | bar: April 2 to April 4
K | 2 | bar: April 3 to April 4
L | 2 | bar: April 4 to May 1
M*** | 4 | bar: April 3 to May 2
N** | 2 | bar: May 3 to May 4
O* | 1 | bar: June 1

## Task List
ID | Task Description | Start | End | Duration | Type | Colour
A | Complete Project Proposal | Oct W1 | Oct W2 | 2 weeks | On-hold
B | Complete Ethics and Data Management Plan | Oct W3 | Oct W3 | 1 week | Documentation
C | Foundation & Prototyping (Audio Loading, Basic Pitch) | Oct W3 | Nov W4 | 6 weeks | Development
D | Basic Tab Generation (Single Notes & Simple Melodies) | Nov W3 | Dec W2 | 4 weeks | Testing
E | Write & Submit Interim Report (10% of grade) | Dec W2 | Dec W4 | 3 weeks | Major deadlines | *
F | Improve Tab Generation (Chords, Polyphonic Audio) | Dec W3 | Feb W1 | 5 weeks
G | Automatic Audio Segmentation Implementation | Feb W2 | Mar W1 | 4 weeks
H | Export Functionality for File Format | Mar W2 | Mar W4 | 3 weeks
I | User Interface Development & Export to MusicXML | Apr W1 | Apr W2 | 2 weeks
J | User Testing & Evaluation Study | Apr W2 | Apr W4 | 3 weeks
K | Buffer Time for Exam Revision & Bug Fixes | Apr W3 | Apr W4 | 2 weeks
L | Final Code Polish & Demo Video Creation | Apr W1 | May W1 | 2 weeks
M | Write Final Dissertation (75% of grade) | Apr W3 | May W2 | 4 weeks
N | Prepare Presentation & Demo for Assessment | May W3 | May W4 | 2 weeks
O | Final Presentation/Demonstration (15% of grade) | Jun W1 | Jun W1 | 1 week